## How To
How To Use This Template
Current Tabs | Assess
Project Information | Change Management Screening
Project Plan | Change Strategy
PCT Assessment | PCT Assessment
Stakeholder Assessment
Change Impact Assessment | Plan
Readiness Assessment | Stakeholder Engagement Plan
Communications Plan | Stakeholder Interview/Survey
Training Plan | Stakeholder Assessment
Testing Plan | Change Roadmap
Completion Checklist | Change Impact Assessment
Deliverables | Readiness Assessment
User List | Program Communications Plan
Site Specific Comms Plan
Reference Data | Training Needs Assessment
Training Curriculum
Adoption Metrics
Adoption Surveys
Mobilize / Sustain
Network Presentations
Stakeholder Coaching
Implementation Playbook
Detailed Implementation Workbook
Site Stakeholder Engagement Presentations
Communications Toolkit
Newsletter Articles
Videos
Emails
Job Aids
Training Videos
Classroom Training Content
Web-based Training Content
Post Go-Live Survey
Feedback Loop
Success Story Communications
Management Communications
Adoption Tracking Dashboard

## Project Info
Project Information
Target Go-Live Date | Date
Site Tool Owner | Name
Site Tool Custodian | Name
Site Power Users | Name, Name
Site Admin | Name
Replication Lead | Name

## Project Plan
<Project / Change Name> Project Plan Template
Pre-Deployment
Step # | T- Week | Project Management | Task | Task Owner | Planned Start Date | Planned Completion Date | Actual Start Date | Actual Completion Date | Status | Risks/Issues | Mitigation Plan | Additional Comments

## PCT Assessment
PROSCI PCT Assessment
Rank each factor on a 1-3 scale:
1 = inadequate
2 = adequate
3 = exceptional
Leadership/Sponsorship factor assessment 1/2/3 |  | Summary:
1. The change has a primary sponsor. |  | Leadership/Sponsorship score | 0
2. The primary sponsor has the necessary authority over the people, processes and systems to authorize and fund the change. |  | Project Management score | 0
3. The primary sponsor is willing and able to build a sponsorship coalition for the change, and is able to manage resistance from other managers and supervisors. |  | Change Management score | 0
4. The primary sponsor will actively and visibly participate with the project team throughout the entire project.
5. The primary sponsor will resolve issues and make decisions relating to the project schedule, scope and resources.
6. The primary sponsor can build awareness of the need for the change (why the change is happening) directly with employees.
7. The organization has a clearly defined vision and strategy. |  | Score Interpretation:
8. This change is aligned with the strategy and vision for the organization. |  | 10-19 High risk/jeopardy - needs immediate action
9. Priorities have been set and communicated regarding this change and other competing initiatives. |  | 20-24 Alert/possible risk - needs further investigation
10. The primary sponsor will visibly reinforce the change and celebrate successes with the team and the organization. |  | 25-30 Strength - should be leveraged and maintained
Score: (total possible is 30) | 0
Project Management factor assessment 1/2/3
1. The change is clearly defined including what the change will look like and who is impacted by the change.
2. The project has a clearly defined scope.
3. The project has specific objectives that define success.
4. Project milestones have been identified and a project schedule has been created.
5. A project manager has been assigned to manage the project resources and tasks.
6. A work breakdown structure has been completed and deliverables have been identified.
7. Resources for the project team have been identified and acquired based on the work breakdown structure.
8. Periodic meetings are scheduled with the project team to track progress and resolve issues.
9. The primary sponsor is readily available to work on issues that impact dates, scope or resources.
10. The project plan has been integrated with the change management plan.
Score: (total possible is 30) | 0
Change Management factor assessment 1/2/3
1. A structured change management approach is being applied to the project.
2. An assessment of the change and its impact on the organization has been completed.
3. An assessment of the organization’s readiness for change has been completed.
4. Anticipated areas of resistance have been identified and special tactics have been developed.
5. A change management strategy including the necessary sponsorship model and change management team model
has been created.
6. Change management team members have been identified and trained.
7. An assessment of the strength of the sponsorship coalition has been conducted.
8. Change management plans including communications, sponsorship, coaching, training and resistance management
plans have been created.
9. Feedback processes have been established to gather information from employees to determine how effectively the
change is being adopted.
10. Resistance to change is managed effectively and change successes are celebrated, both in private and in public.
Score: (total possible is 30) | 0

## Stakeholder-Definitions
Stakeholder Action Plan - Definitions
Stakeholder Engagement Score
| Rank | Primary Descriptor | Current Mindset
| 1 | Awareness | Encounters change and realizes change is imminent. Awareness of Digital Manufacturing.
| 2 | Understanding | Accepts nature and intent of change. Grasps why Digital Manufacturing is important, knows who to go to with questions on the project, understands how it ties to strategic objectives.
| 3 | Acceptance | Tests the new concepts and change implications. Articulates willingness to perform as the change requires. Knows the project impacts and when they will be involved in the change. Supportive of change and actively/proactively demonstrates needed behaviors.
| 4 | Commitment | Articulates the change as norms and articulates his/her personal ownership of the change. Sees the change as an accepted norm and is committed to the change journey. Seeks opportunities for continuous learning and growth, proactively initiates discussions.
| 5 | Owns Change | Participates in facilitating change. Changes behavior or procedures to support process changes. Takes personal ownership, is committed to implementing and championing the change.
Business Impact
| Rank | Primary Descriptor | Standard / Test
| 1 | Indirect Influencer | May have some impact on decisions but can't influence directly
| 2 | Contributor | Attends the workshop and contributes to the end deliverable
| 3 | Direct Influencer | Has key influence on decision making
| 4 | Primary Decision Maker | Makes final decision or has veto power
Priority Ranking
Use Priority Ranking to guide how you will spend your outreach time. This priority ranking will help the team spend the right amount of time and energy on each relationship.
| Rank | Primary Descriptor
| 1 | Highest Priority
| 2 | Maintain/Grow
| 3 | Longer Term Focus

## Stakeholder Assessment
|  |  |  | Location |  |  |  | Target
Last Name | First Name | Position | Role | Region | Business Unit | Location | Assessment Method | Current Commitment | Starting Commitment | Commitment Post-Engagement | Commitment Sprint End | Business Impact | Priority Ranking | Primary Relationship Owner | Comments
Doe | John | Senior Vice President Global Operations | Global Sponsor | Global | Chemicals | EMHC |  | 1 |  |  |  | (4) Primary Decision Maker | 1 | Change Manager Name
Doe | Jane | Technical Specialist |  | Americas/NA | EMRE | EMHC | Survey |  | 3 |  |  | (4) Primary Decision Maker | 2 | BVM Name
Owns Change
Commitment
Acceptance
Understanding
Awareness
Note on H3: Hewson, Sarah E.: Specific to the site
Note on O3: Hewson, Sarah E.: PICKLIST 1 = Highest Priority 2 = Maintain/Grow 3 = Longer Term Focus

## Change Impact Instructions
Change Impact Assessment Instructions
The Change Impact Assessment (CIA) is fundamental to understanding the scale and types of business changes that the implementation will cause. This CIA will capture key changes and will help define the way that employees need to work in the future so that they can support the new and/or updated processes and system changes. Please follow the steps below to update the CIA (Examples are provided on the "Change Impact Assessment" tab).
| Step 1: | Capture impacted audience information:
- List stakeholder groups and/or roles by specific change item (column C)
- Mark which location(s) the stakeholder groups and/or roles are located (column D)
- Included approximate headcount (number of users) impacted by this change (column E)
| Step 2: | Identify what's changing by capturing the current state (column F) and the future state (column G).
| Step 3: | Analyze the "As-Is to To-Be" for each type of change by referencing process documents, process flows, delivery teams, SMEs, etc.
Process Change (column H)
Summarize the current state, future state, and the specific impacts of those changes from a process perspective.
System/Technology Change (column I)
List the systems that are impacted, then summarize the current state, future state and specific impacts of the technology changes.
People/Organizational Change (column J)
Summarize current state, future state and specific impacts to people, organizational, or the culture (role, skills, behaviors, reporting structure).
| Step 4: | Determine Overall Level of Impact for this change to the user by considering the following criteria (column K):
High - Complex business changes and large audience impacts that may require several addition actions beyond training and communications and anticipate high resistance to adoption. Some examples include new processes being introduced, complex transactions, new workflows or new individuals being introduced into the process.
Medium - Moderate business changes that may require a few additional actions beyond training and communications and anticipate low to moderate resistance to adoption. Some examples include new steps in a process, steps that need to be completed in a different order, or transactions that now require additional information.
Low - Minimal business changes that should be easy to adopt with training and communications and anticipate low to no resistance to adoption. Some examples include manual processes that are now automated and transactions that are not different from legacy systems.
| Step 5: | Identify different Change plan actions to increase readiness that should be considered based on this change in each of the following columns (L-N) as needed:
Leadership: specific leadership involvement to support and champion the change (e.g. leadership forum, 1:1, department meeting)
Communications: include specific message(s) or type of communication method (e.g. email, live meeting, webcast, newsletter, posters)
Training Methods/ Type: include if training is needed and the best method/type of training to educate the change (e.g. classroom, web-based, job aid, video, gamification)
| Step 6: | Provide name/source, date and comments to track changes in the Data Control section (columns O-Q)
| Step 7: | Save
For an example, please see the Change Impact Assessment for the T1BP Strategic Planning Tool Project:
https://ishareteam4.na.xom.com/sites/RSIT/IoT/Templates/T1BP%20Strategic%20Planning%20Tool%20Project%20-%20Change%20Impact%20Assessment.xlsx

## Change Impact Assessment
Change Impact Assessment
Impact Description | [5 empty] | Impact Areas: Change Summary | [10 empty] | Change Management Actions |  |  | Data Control
ID | Affected Stakeholder Group(s) | Site(s) / Location(s) Affected | Number of People Affected | Current State | Future State | Process | System | Tools | Job Roles | Performance Reviews | Reporting Structure | Location | Mindset Attitudes Beliefs | Critical Behaviors | Compensation | Overall Level Impact (High, Medium, Low) | Leadership Actions | Communications | Training / Skill Requirements | Date | Source | Comments
Note on H4: Is there a change to the way they do their job - the process they follow?
Note on I4: Are they using a new application or system to peform their job?
Note on J4: Are they using a different physical tool? E.g. Did they used to use pencil and paper and are not using an iPhone to tilize a mobile app?
Note on K4: Does this require a person to add new functions or change some of the existing functions of their current job?
Note on L4: Does this change update how performance is assessed?
Note on M4: Is the organization's reporting structure changing?
Note on N4: Is their physical location changing? e.g. an office move to a new site
Note on O4: Does this change some of their fundamentals beliefs about their work, role, responsibilities?
Note on P4: Does this impact critical behaviors like safety? E.g. They are now using a wireless sensor to perform gas tests when they used to do this manually with a gas test prior to issuing permits.
Note on Q4: Does this impact the group's compensation / pay?

## Readiness Assessment
Readiness Assessment
<This is an optional form> Use this form to document/track required actions prior to cutover.
Activity | Description | CM Actions required | CM Responsible for actions | CM Status
Functionality or activity TITLE | Describe required functionality or activity. | Describe requirements for MoC (no Action, Inform users, etc…) | Name of CM advisor responsible for activities | Complete

## Communications Plan
Communications Plan
Date | Communication Channel | Topic | Key Message | Primary Audience | Secondary Audience | ADKAR | Deliverable Creator | Deliverable Sender | Deliverable Status | Comments
Note on D2: Kauffman, Patience: Example Channels: F2F, Functional, Manager, Email, Newsletter, Team Meeting, etc.

## Training Plan
Training Course | Description: Training Topics | Training Audience | Duration | Link to material | Training Format (Video, Job Aid, Training Deck, etc.) | Training Delivery Channel | Item Status | Additional Comments
EXAMPLE: Digital Procedures Overview | Creating new, unwritten procedures using the Skelta Digital Procedures tool | All | 30 min | Creating a procedure, populating form fields, Skelta environment | Job Aid - PPT | ILT, Self-Study | Review | Using source material ExxonMobil Digital Procedures
Example: Downloading the Work Tasks Pro App |  | All | 10 minutes |  | Job Aid - PPT | QRG, Self-study | In Progress
Learning Methods: |  | Roles to Train (examples provided)
ILT |  | Site Admin
Job Aid |  | Power Users (Name might change)
Quick Reference Guide (QRG) |  | Role X
Micro-Learning |  | Role Y
…

## Testing Plan
Phase | Duration | Start Date | End Date | Testing Task (example tasks provided) | Users
Planning Phase |  |  |  | Performance test assessment
Develop Test Plan
Test Plan review by Project Team; update and redistribution of documents following review
Identify Testing Network members
Development Phase |  |  |  | Create Test Case for Acceptance Test
Training and support for XXX to testers
Create Smoke Test
Create Production Verification Test
Developing Performance Test
Developing Regression Test
Execution Phase |  |  |  | User test for XXX functionality
User test for YYY functionality
Regression Test
Acceptance test for XXX functionality
Acceptance test for YYY functionality
Defect fix retest, test re-execution
Creating Test Report.
Execute Production Verification Test
Close Out Phase |  |  |  | Transfer outstanding defects to next wave/backlog
Automation of Integration Tests for Regression Test purpose

## Completion Checklist
Implementation Completion Checklist
Criteria | Definition of Complete | Measure of Utilization | Status | Date Completed
1
2
3
4
5
6
Example
| Technical and Business CoE support is available | Users are aware of the proper EMIT support channels | Complete
| Security and Permissions are appropriately assigned | Individual use of Technology does not require approval above FLS Level | In Progress
| Training support documentation is available | Support materials are posted online and all necessary employees have access | Not Started
| 100% of users have completed required training | All employees with roles identified in the training plan have been successfully trained on the DP application and associated process changes (if applicable) | Not Started
| Site work practice documentation has been updated | Any changes to site work practices as a result of digital scaffold have been captured in the site's documentation | Not Started
| Benefits capture plan has been defined | There are business practices in place to collect the identified Benefits Metrics and report to the Project Manager on a Quarterly basis | Not Started
| 100% of barriers are logged through the DP application | = (# Barriers Captured in DP)/ (# Barriers Captured in DP + # Barriers Not Captured in DP)) | Not Started
| Site stewardship is in place to ensure ongoing application | Site has taken ownership over ongoing usage of DP | Not Started
| Technology is in use and is the default option versus alternatives (manual processes) | Sufficient change management efforts have been completed so that users do not default back to working outside the system for barrier logging, permit management, scheduling | Not Started
| Legacy systems have been decommissioned (if applicable) | The solution used for DP functionality (permitting, scheduling, barrier capture) have been replaced; DP is the sole system to manage these capabilities. | Not Started
| ISRMP responsibilities have been reviewed with Site Tool Owner | Site Tool Owner understands ISRMP responsibilities | Not Started

## Resistance Management
Resistance Management Plan
<This is an optional form> Use this form to document/track required actions prior to cutover.
Stakeholder Group | Impact Level | Resistance Level | Perceived Benefits | Anticipated Resistance | Potential or Real? | ADKAR Barrier | Resistance Reason | Resistance Approach | Mitigation Plan | Assigned to | Resistance Status
Name of Stakeholder Group or individual stakeholder | The level of influence or impact of this individual or group | Anticipated level of resistance |  |  |  |  | Cause or reason for resistance | Recommended method for dealing with the resistance to change | Action(s) to address this Stakeholder Group | Name of person responsible for activities | Current status of Resistance (i.e New, In progress, Complete)

## Deliverables
Deliverable | Status | Location Link | Date Completed
Change Screening Tool
Change Strategy
Stakeholder Engagement Plan
Stakeholder Analysis
Change Roadmap
Change Impact Assessment
Change Readiness Assessment
Program Communications Plan
Site-Specific Communications Plan
Training Needs Assessment
Training Curriculum
Adoption Metrics
Adoption Surveys
Network Presentations
Stakeholder Coaching
Implementation Playbook
Site Stateholder Engagement Presentations
Communications Toolkit
Newsletter Articles
Videos
Emails
Job Aids
Training Videos
Classroom Training Content
Web-Based Training Content
Post Go-Live Survey
Feedback Loop
Success Story Communications
Management Communications
Adoption Tracking

## User List
Name | UserName / LANID | email | Company | Site | Control Center | Unit Name | Permissions/Role | Comments | <This is an optional form> Use this form to document required user roles for new tool.

## Reference Data
Stakeholder Data
Lists - Descriptions | Drop-downs
[5 empty] | UPDATE |  |  | UPDATE
|  |  |  | Relationship Owners Table |  |  | Business Units Table
Relationship_Quality |  | Goal Priority |  |  | Name |  |  | Name
(1) Awareness | 1 | High |  | Enter all potential Relationship Owners |  | Rel Owner 1 | Enter each unique Business Unit | Chemicals | Business Unit 1
(2) Understanding | 2 | Medium |  |  |  | Rel Owner 2 |  | EMIT (REIT) | Business Unit 2
(3) Acceptance | 3 | Low |  |  |  | Rel Owner 3 |  | EMRE | Business Unit 3
(4) Commitment | 4 |  |  |  |  | Rel Owner 4 |  | Refining | Business Unit 4
(5) Owns Change | 5 |  |  |  |  | Rel Owner 5 |  | EMIT | Business Unit 5
|  | Yes or No | [5 empty] | UCD | Business Unit 6
Business_Impact |  | Yes | [5 empty] | Engineering Services | Business Unit 7
(1) Indirect Influencer | 1 | No | [5 empty] | RSO
(2) Contributor | 2 | [6 empty] | Global SHE
(3) Direct Influencer | 3 | Frequency
(4) Primary Decision Maker | 4 | Weekly
Biweekly
Priority Ranking |  | Monthly
Highest Priority | 1 | Quarterly |  |  |  |  | Assessment Method
Maintain/Grow | 2 | Semi-Annually |  |  |  |  | Survey
Longer Term Focus | 3 | Annually |  |  |  |  | Face-to-Face Interview
Telecon Interview
Assessment
Highest Priority | 1 |  | Status
Maintain/Grow | 2 |  | Not Started
Longer Term Focus | 3 |  | In Progress
Complete
Starting/Current commitment
Awareness | 1
Understanding | 2
Acceptance | 3 |  | Assessment Method
Commitment | 4 |  | Survey
Owns Change | 5 |  | Face-to-Face Interview
Telecon Interview
Change Impact Assessment
Lists - Descriptions | Drop-downs
Impact Areas: Change Summary
Low | 1
Medium | 2
High | 3
PCT
Lists - Descriptions | Drop-downs
Scores
Low | 1
Medium | 2
High | 3

## Stakeholder Assessment ADKAR
Profile Information |  |  |  |  | Location |  |  |  | Assessment | [6 empty] | Target
Stakeholder Type | Last Name | First Name | Position | Role | Region | Business Unit | Location | Assessment Method | Awareness | Desire | Knowledge | Ability | Reinforcement | Commitment Post-Engagement | Commitment Sprint End | Current Commitment | Starting Commitment | Business Impact | Priority Ranking | Primary Relationship Owner | Comments
| Doe | John | Senior Vice President Global Operations | Global Sponsor | Global | Chemicals | EMHC
| Doe | Jane | Technical Specialist |  | Americas/NA | EMRE | EMHC | Survey
Note on I3: Hewson, Sarah E.: Specific to the site
Reinforcement
“I will continue to …”
Ability
“I am able to …”
Knowledge
“I know how to …”
Desire
“I have decided to…”
Awareness
“I understand why…”